## DT App-369links
S.No | Task Description | Priority | Start Date | End Date | Assigned To | Guide | Status
1 | Migration from india digital ocean to us digital ocean | P1 |  |  | Meenakshi |  | Completed
2 | create a signed exe for sharing with Steve | P1 |  |  | Meenakshi |  | Completed
3 | Testing New App on Us server | P1 |  |  | Meenakshi |  | Completed
4 | Fix multiple tray in electron | P1 | 2023-10-02 | 14-02-2023 | Meenakshi |  | Completed
5 | create a new installer and uplod the new exe to microsoft store for Us Server | P1 | 15-02-2023 | 15-02-2023 | Meenakshi |  | Completed
6 | Push the new exe to microsoft store for IN Server(for multiple tray issue fixed) | P1 | 15-02-2023 | 15-02-2023 | Meenakshi |  | Completed
7 | Change app downlod buttons on header to icons and add urls on both bharatcpbx and 369links.com and Us server as well | P2 | 19-02-2023 | 19-02-2023 | Meenakshi |  | Completed But Not tested and uploaded on servers
8 | Call Waiting Module on facelifted App | P1 | 21-02-2023 | 21-02-2023 | Meenakshi |  | Completed | 369Links-DT-Windows-India
9 | Conference module | P1 | 22-02-2023 | 25-02-2023 | Meenakshi | Anurag | In progress
10 | Sync up Messages/IM with Mobile App from Database (need help from Saji) | P2 |  |  | Meenakshi | Saji | Pending
11 | Sending Files in Chats | P2 |  |  | Aleem |  | Pending
12 | Resize DT App (GUI) | P1 |  |  | Aleem | Meenakshi | Released for testing/ Improvements
13 | DT App revamp(without monster UI Code only using apis) | P1 | 13-02-2023 | 22-02-2023 | Aleem | Meenakshi/Anurag | Released for testing/ Improvements | 369Links-DT-Windows-India
14 | Bug fixes | P1 |  |  | Ankita/Arpita/Sarika
15 | Clear cache/localstorage/sessionstorage when we hit login page | P3 | 13-02-2023 | 16-02-2023 | Arpita | Aleem | Completed
16 | Know how of code base | P3 | 13-02-2023 | 13-02-2023 | Sarika | Aleem | Completed
17 | Presence does not reflect sometimes on first load, test and fix the bug | P3 | 14-02-2023 | 16-02-2023 | Sarika/Aleem | Aleem | Completed
18 | The DT App is getting disconnected in less than 15 mins (Handled Login) | P1 | 17-02-2023 | 20-02-2023 |  |  | Completed
19 | Reconnect the app after its disconnected without page resfresh,only ip should get refreshed | P1 | 18-02-2023 | 18-02-2023 | Meenakshi |  | Completed
20 | Update the code for Point 19,on us and india server and test | P1 | 18-02-2023 | 18-02-2023 | Meenakshi |  | Completed
21 | Recent Not working -call logs not getting generated | P1 | 20-02-2023 | 20-02-2023 | Meenakshi |  | Completed
22 | Installer should show up on program start up | P2 |  |  | Meenakshi |  | Pending
23 | Change the names of the Apps in Microsoft App Store as suggested by Yuvi For India - 369links-IN For US - 369links-US | P1 |  |  | Meenakshi |  | Completed | 369Links-DT-Windows-Us/India
24 | GUI improvements for Revamped DTApp | P2 | 23-02-2023 |  | Ankita/Arpita/Sarika | Aleem | Released for testing
25 | Documentation | P1 |  |  | Santosh/Anjali/Saumya | Yuvi | In progress | Adding all the details in support page
26 | DT app adapation to Mobile app | P1 |  |  | Aleem |  | In progress
28 | Make Revamped app work on freshdesk | P1 |  |  | Aleem |  | In progress/Waiting on Freshdesk

## Integrations
| Status | Priority | Start Date | End Date
Salesforce | Pending
Hubspot | Pending
Zoho | Pending
Zoom | Pending
Telesoft | Pending | P1
Freshworks | Pending | P1
Microsoft Teams | WIP | P1
Zoom | Pending | P1
One Bill | Pending | P1

## Other Changes
S.No | Task Description | Priority | Start Date | End Date | Assigned To | Guide | Status | Testing
1 | FreshDesk Integration with our new DT Revamp App (can be done only when point no.12 in DT App tab is done) | P2 |  |  | Meenakshi/Aleem | Meenakshi | In progress
2 | Functionalities
a | Update Login Page for Monster UI |  | 13-02-2023 | 20-02-2023 | Ankita | Aleem | In progress
b | Call Center App | P2 |  |  | Arpita | Anurag | Pending
c | Recording App Not working |  | 13-02-2023 | 14-02-2023 | Meenakshi | Saji | Completed
d | Call Hunting |  | Arpita |  | Yuvi | Anurag | Pending
3 | System Maintainence
| Clean up for unnecessary apps on bharatcpbx and 369links.com | P3 |  |  | Meenakshi | Anurag | Pending
4 | Github code merge changes(DT App) (Friday) | P3 | 2023-10-02 | 2023-10-02 | Pavitra | Aleem | Completed
5 | Cloning DT App and Monster UI App from Github and run on local system |  | 2023-10-02 | 2023-10-02 | Sarika/Pavithra | Ankita/Arpita | Completed | Completed
6 | Created seperated DTRevamp App on Github
7 | Revamp the bharatcpbx DT App similar to 369links
8 | create a new installer for facelifted DT App for BSNL

## One bill Integration
S.No | Task Description | Priority | Start Date | End Date | Assigned To | Guide | Testing
1 | Onebill integration | P1 |  |  | Meenakshi | Anurag/Saji | Yallapa(commercial point) and Yuvi (Testing point)
a | Account Creation
b | Bill Generation
c | CDRS
d | Pre Paid
e | Post Paid
f | Support Desk
g | Check CTI integration for Support

## BSNL Bug List
S.No | Task Description | Priority | Start Date | End Date | Assigned To | Guide | Status | Testing | Remarks
1 | "Fix issue coming on Bharatcpbx DT App (Manipal): 1.Message is not coming once third person cuts the call 2. Third call if accepted then the person who has accepted the call cant hear" | P1 | 15-02-2023 | 23-02-2023 | Sarika | Meenakshi |  | Completed | Could Not reproduce the bug,when testing was working fine

## Support
S.No | Task Description | Priority | Start Date | Finish Date | Effort Estimation | Assigned To | Guide | Testing
Testing
1 | DT US app testing by using VPN | P1 |  |  | Everyday | Aurifa/anjali/saumya | yuvi
2 | DT US app testing without VPN | P1 |  |  | Everyday | Aurifa/anjali/saumya | yuvi
3 | tmp.369links.com testing by | P1 |  |  | Everyday | Aurifa/anjali/saumya | yuvi
4 | DT App sanity testing | P1 |  |  | EVeryday | Aurifa/yuvi | yuvi
5
Testing Documentation
1 | BharatCPBX | P1 | 2023-02-01 | 2023-08-03 |  | Aurifa/Anjali/Saumya | Yuvi
2 | 369links | P1 | 2023-02-01 | 2023-08-03 |  | Aurifa/Anjali/Saumya | Yuvi
Support activities
1 | Preparing girls on support | P1 | 13-02-2023 | 25-02-20233 | 1week | Yuvi | Anurag
a | Training girls on dashboard |  | 13-02-2023 |  |  | Yuvi
b | SIP PHONE & GS WAVE LITE TRAINING
c
2 | Ecs369 forum ( issues list ) | P1 | 13-02-2023 | 2023-08-03 |  | Santosh/Yuvi | Yuvi
3 | Documentation
Automation
1 | 369links desktop app automation | P1 |  |  |  | Aurifa | Yuvi
2 | Dashboard 369links automation | P1 | 13-02-2023 | 18-02-2023 | 1week | Aurifa | Yuvi
3 | all servers ping automation | P1 | 13-02-2023 | 18-02-2023 | 1week | Aurifa | Yuvi